## Slide 1
Weekly Review – IT SP A&W
24.12.2025

## Slide 2
Major Projects:
SP-A&W
Accessibility guidelines in corporate website
Compliance with the Accessibility Standards and Guidelines for Banking Sector
SIT is in progress
Tentative Roll out date 23.01.2026
Enhanced Look and Feel of web pages and enhance omnichannel experience.
ISD Security Review is in progress
Tentative Roll out date 30.12.2025
REVAMP OF YONO SECTION ON BANK’S CORPORATE WEBSITE
IMPLEMENTATION OF
GEN AI FEATURES IN eMEETING APPLICATION
Generation of brief summary of agenda items.
Cross referencing based on a keyword and generation of AI powered summary on any specific topic from the uploaded agenda items.
AI based search features on the uploaded documents.
Demand Impact Assessment is in progress

## Slide 3
Major Projects:
SP-A&W
IAP – RFCA
Redevelopment of existing application on IAP.
Development in progress
CUG: Jan 2026
An Application for the automation of the RBI tranche III DCT testing.
Facilitate faster and accurate reporting to Compliance Dept. CC for onward submission to RBI.
Development in progress
(~10%)
31.03.2026
Automation of RBI TRANCHE III testing for IAD

## Slide 4
Major Projects:
Demands summary
SP-A&W
  Open DEMAND - 87
Chart: Phases
Chart: Phases
| SIT | Pause/Stop Initiated | CCC/Buisness sign off | UXD | ISD/E&TA | UAT | Development is in Progress | Planning Stage | Pre-demand Stage
Phases | 1 | 1 | 9 | 2 | 6 | 6 | 33 | 11 | 18

## Slide 5
Major Projects:
Demands summary
Chart: Demand Stages
| SIT | Pause/Stop Initiated | CCC/Buisness sign off | ISD/E&TA | UXD | UAT | Development is in Progress | Planning Stage | Pre-demand Stage
Series 1 | 1 | 1 | 9 | 6 | 2 | 6 | 33 | 11 | 18

## Slide 6
Major Projects:
Chart: 
| Planning Stage | Pre-demand stage
Series 1 | 11 | 18
Days Wise Pendency | Count
> 90 days | 0
61-90 days | 0
31-60 days | 1
0-30 days | 28
Demand Stages
Pre-demand & Planning Stages

## Slide 7
Major Projects:
Chart: 
| <30 Days | 31 - 60 Days | 61-90 Days
Series 1 | 16 | 16 | 1
Days Wise Pendency | Count
61-90 days | 1
31-60 days | 16
0-30 days | 16
Total | 33
Development in progress
Development in Progress

## Slide 8
Demands summary
Application Name | > 90 days | 61-90 days | 31-60 days | < 30 days | Total
IAD | 1 | 0 | 16 | 49 | 66
Websites & Meetings | 0 | 0 | 1 | 15 | 16
SP-A&W
DAYS WISE DEMAND BUCKET

## Slide 9
Stagnation Demand
SP-A&W
Days Wise Pendency | Count
>90 days | 1
31-60 days | 17
0-30 days | 67
Total | 85
Major & Support
Projects
Stagnation Period

## Slide 10
DEVIATIONS:
SP-A&W
nil

## Slide 11
Review of ATR:
SP-A&W
I
A
D
ACB Meeting dated 20.08.2025
Branch One view platform
Timeline for compliance
30.09.2025
ACB Meeting dated 14.10.2025
Is aUDIT
FOUR OBSERVATIONS ARE OPEN

## Slide 12
Pendency pertaining to Audit Observations
SP-A&W
Name of Audit (Period) | Audit Report Date | Compliance Date oAudit | 1st ATR Submission Date | 2nd ATR Submission Date | 3rd ATR submission Date | 4th ATR submission Date | Remarks If Any
IS Audit (2025-26) | 17.05.2025 | 28.06.2025 | 08.07.2025 | 01.09.2025 | 15.10.2025 | 15.12.2025 | 4 observations are open. (Detailed remarks are provided in slides 20 & 21)
Cyber Security Audit (2025-26) | 07.07.2025 | 13.09.2025 | 18.09.2025 | 15.12.2025 | - | - | *Cyber Security Audit 2025-26 is forced closed by IAD on 28/11/2025 with 2 residual observations, which are carry forwarded to running cyber security audit.
CSR (2024-25) | 11.04.2025 | - | - | - | - | - | CSR 2024-25 for Special Projects- Audit & websites Applications has since been closed.

## Slide 13
Pendency pertaining to Audit Observations
SP-A&W
IS AUDIT 2025-26
SI No | Risk Perception | Total No of Audit observations | 1st ATR Compliance (08.07.2025) | 2nd ATR Compliance (01.09.2025) | 3rd ATR Compliance 15.10.2025 | Pending Observations | % of Compliance
1 | HIGH | 63 | 28 | 24 | 18 | 4 | 94
2 | MEDIUM | 34 | 23 | 7 | 6 | 0 | 100
3 | LOW | 15 | 13 | 0 | 2 | 0 | 100
 | TOTAL | 112 | 64 | 31 | 26 | 4 | 98
SI No | Risk Perception | Total No of Audit observations | 1st ATR to be Complied (Tentative 10.09.2025) | Pending Observation | % of Compliance
1 | HIGH | 10 | 10 | 0 | 100
2 | MEDIUM | 12 | 10 | 2 | 83
3 | LOW | 2 | 2 | 0 | 100
 | TOTAL | 24 | 22 | 2 | 91
CYBER SECURITY AUDIT 2025-26

## Slide 14
EOL/EOS/EOEs STATUS AS ON 31.08.2025
SP-A&W
nil

## Slide 15: THANK YOU

## Slide 16
Appraisal for Major Projects
Website & meetings
1. Accessibility guidelines implementation in SBI corporate website
  To ensure compliance with the Accessibility Standards and Guidelines for Banking Sector, which aims to promote equal and non-discriminatory participation for individuals with disabilities.
  Bank has engaged M/s CABE Foundation for an accessibility audit. The audit identified deficiencies on multiple pages from an accessibility perspective. The auditor has identified 119 such observation that are required to be fixed 114 observations have been fixed and 113 have been closed by the auditor and remaining is under process .
  Current Status - Development is in progress. 90% completed. Tentative date of completion – 15.12.2025
2. Capturing of feedback at bank website
  Compliance requirement of Ease 8.0 under metric Id 14.01.02. Under this demand requirement the creation of feedback form for the customer accessing the portal was mandated and the same is being developed as per the demand.
  Feedback will help to further improve the bank corporate website.
  Current Status – Rolled out on 18.11.2025

## Slide 17
Appraisal for Major Projects
Website & meetings
3. eMeeting- Implementation of GenAI features
  Has raised the captioned demand and a support demand on Analytics department for developing the AI rule engine/model.
  Analytics department has conducted a preliminary analysis and advised the feasibility.

## Slide 18
Appraisal for Major Projects
IAD
IAP-RFCA: Risk Focused Credit Audit for audit of credit intensive branches. CUG – Jan 26
  Risk Focused Credit Audit is an application used for audit of credit intensive branches for Credit and Control Risk Assessment and follow-up of risk mitigation.
  Application is being redeveloped in IAP-Integrated Audit Platform using latest technologies.
  This redevelopment will facilitate easy integrations with other IAP Modules.
  IAP-RFCA is integrated with EDMS to store the evidence uploaded by the Auditee Unit

## Slide 19
Review of ATR:
IAD
ACB – Meeting Dated 20.08.2025
Observation No. | Brief Content | IT Dependency statement in the agenda item EA note | Talking Point/ update from IT AOs | Timeline for Compliance
11 | “Branch One View” platform | "URF for IT priority demand relating to Branch One View raised on 10.10.2024 On 24.10.24, IAD SP 2 cell, GITC has advised the constraints in delivery within the desired timelines on account of unavailability of sufficient developer resources with them. IAD SP 2 cell requested for initiating pause for Branch One View Portal and New IAD Intranet site, as the same shall require hiring of resources with required skills, for which they have informed us having initiated a note. In this regard, DMD (IA) has taken up with DMD (IT) vide letter no. IAD/IT/2024-25/2460 dated 05.11.2024 for expediting augmentation of requisite resources to support expeditious development of the “Branch One View” portal. This initiative is aimed at ensuring compliance with the ACB action point and fulfilling the Committee’s directive without further delay. Given the current constraints, the process of resource acquisition may extend beyond the expected timeline. Hence, extension of time upto 01.02.2025 may please be accorded. Regarding WBCAS, to review and appropriately modify the penalty clauses for fee reduction or levying penalty on the Concurrent Auditor, as the case may be we request an extension of timeline upto 01.02.2025. The incorporation of revised penalty clauses in Service Level Agreement (SLA) will be carried out once the proposed changes are vetted and cleared by the Law department. The Appropriate Authority for permitting timeline within 7 days of allocation of action point is the Vertical Head. Accordingly, approval has accorded for extension of timeline upto 01.02.2025 Extension in timeline upto 31.12.2025 was approved by ACB in its meeting dated 05.02.2025 vide Agenda No. D-IA-1." | Branch One View Dashboard portal development has been taken up in two phases. The status is as under: 1) Branch One View Phase I - DM2025016691 Status - Rolled out in Production in 27.05.2025. 2) Branch One View Phase II - DM2025059504 Status - Development Completed and Promoted to UAT by BU-IAD on 14.08.2025. Tentative Roll out Date is 30.09.2025 (The point mentioned for WBCAS is not within the purview of the above Demand) | 30.09.2025

## Slide 20
Review of ATR:
IS Audit
ACB – Meeting Dated 14.10.2025
S.No. | Observation Brief | ATR Submission Date | Whether Complied/ In-progress | Current status
1 | During the review of the SCD Scan report for the Month of March 25 it is observed that SCD Compliance Scan Failed for the following 9 servers:- IP Address Type Applications Device Criticality Environment Zone 10.176.47.196 Database SBICOIN Medium DR MZ 10.189.197.8 Database ITFO Website Consolidation Medium PR MZ 10.189.39.253 Application_Server OARPS Medium DR MZ 10.189.34.68 Application_Server SBICOIN High PR MZ 10.189.34.69 Application_Server SBICOIN High PR MZ 10.189.34.70 Application_Server SBICOIN High PR MZ 10.176.18.186 Web_Server AMLOCK TM Medium DR MZ 10.189.46.143 Web_ | ATR submitted on 15.12.2025 | Complied | Since Complied

## Slide 21
Review of ATR:
IS Audit
ACB – Meeting Dated 14.10.2025
S.No. | Observation Brief | ATR Submission Date | Whether Complied/ In-progress | Current status
2 | Public WiFi detection mechanism is not implemented in the application. There is no warning notification issued informing users of potential dangers of connecting to public WiFi by sharing their personal credentials like phone number. | ATR submitted on 15.12.2025 | Complied | Since Complied
3 | Tunneling is not implemented in eMeeting in violation of IS Policy v10 Section 18.3.1. Once downloaded through Intunes, the application communicates with its servers directly through internet and not via Intune tunnel. |  | In progress | Permanent approval for continuation of application without tunnelling is being put up to competent authority for closure of observation. Timeline: 31.01.2026
4 | Tunneling is not implemented in iMeeting in violation of IS Policy v10 Section 18.3.1. Once downloaded through Intunes, the application communicates with its servers directly through internet and not via Intune tunnel. |  | In progress | Permanent approval for continuation of application without tunnelling is being put up to competent authority for closure of observation. Timeline: 31.01.2026